## Instagrandmas
Epic Name | Epic Duration | Num of Story | Start Date | End Date | Story No Point | Story Has Points
CLOSED - Urgencies - Support and Bugs (Feb 2019) | 21 | 51 | 2019-01-30 18:35 | 2019-02-27 21:12 | 51 | 0
Boards & IG Likeshop Migration (Legacy Migration Phase 1) | 58 | 77 | 2019-01-07 17:42 | 2019-03-27 19:14 | 77 | 0
Move Custom Requests to Instagram Backend (Likeshop/Gallery importing) | 22 | 3 | 2019-06-10 15:05 | 2019-07-09 18:22 | 3 | 0
Content Rights v2 Phase 1 (Legacy Migration Phase 2.5) | 23 | 48 | 2019-07-01 14:35 | 2019-07-31 14:17 | 48 | 0
IG UGC v2 (Legacy Migration Phase 3) | 173 | 63 | 2019-01-28 17:44 | 2019-09-25 16:12 | 46 | 17
Hashtag monitor Integration (Legacy Migration Phase 4) | 228 | 57 | 2019-01-06 20:43 | 2019-11-20 13:39 | 38 | 19
Move Custom Requests to Instagram Backend (RIQ Uploads/Minor tasks) | 42 | 10 | 2019-05-13 17:56 | 2019-07-09 16:12 | 10 | 0
Social Connections Page + FB Connection Migration (Legacy Migration Phase 4.4) | 73 | 51 | 2019-11-11 20:42 | 2020-02-19 18:30 | 37 | 14
Support for Instagram @creators usage | 34 | 11 | 2019-12-01 16:19 | 2020-01-16 18:31 | 11 | 0
Formulas:
Epic Duration = NETWORKDAYS([Start Date],[End Date])

## DontPanic
Epic Name | Epic Duration | Num of Story | Start Date | End Date | Story No Point | Story Has Points
Google Shopping Feed | 30 | 2 | 2019-02-27 21:16 | 2019-04-09 21:05 | 2 | 0
Instagram Stories Import - Boards for Stories and Swipe-ups Shared Functionality (Target: Feb 28) | 30 | 14 | 2019-01-20 15:31 | 2019-03-01 18:19 | 14 | 0
Implement Swipe Up tracking for Stories in Scheduler and Track in Stories (Target: Feb 28) | 28 | 18 | 2019-01-28 19:03 | 2019-03-06 19:35 | 18 | 0
Boards for story cards (Target: Feb 28) | 103 | 78 | 2018-10-22 18:58 | 2019-03-13 20:12 | 78 | 0
E-Mail Template options into Spirit Galleries | 8 | 4 | 2019-03-26 19:38 | 2019-04-04 12:05 | 4 | 0
Likeshop Widget (Legacy Migration Phase 2) | 8 | 2 | 2019-03-28 13:51 | 2019-04-08 12:59 | 2 | 0
Global Spirit Gallery Enable/Disable | 5 | 5 | 2019-03-31 19:51 | 2019-04-05 13:33 | 5 | 0
Implement 360 Report | 38 | 33 | 2019-04-04 18:54 | 2019-05-27 21:30 | 33 | 0
Pinterest Auto Publish (Web and Mobile) Phase 1 | 57 | 124 | 2019-05-29 12:45 | 2019-08-15 17:43 | 106 | 18
LikeShop Pages in 360 Report | 13 | 5 | 2019-06-05 16:31 | 2019-06-21 12:51 | 5 | 0
Pinterest Platform | 201 | 115 | 2018-11-20 11:31 | 2019-08-27 16:27 | 97 | 18
Pinterest Auto Publish Post Release (Web) | 25 | 13 | 2019-08-20 17:15 | 2019-09-23 20:11 | 13 | 0
Pinterest Platform Post Release | 58 | 56 | 2019-08-20 19:55 | 2019-11-07 13:02 | 56 | 0
Trends groups in Visual IQ | 47 | 79 | 2019-09-17 03:06 | 2019-11-20 12:31 | 79 | 0
Set Up Ads Platform product | 8 | 6 | 2019-11-11 15:43 | 2019-11-20 12:32 | 6 | 0
Line up Our own Pinterest Stats w/ Pinterest Stats | 24 | 18 | 2019-11-13 19:12 | 2019-12-16 18:30 | 18 | 0
Ads Platform - Your Ads | 51 | 77 | 2019-11-18 21:04 | 2020-01-27 20:36 | 74 | 3
Product UI - Hide Photo from Product Page Widget | 5 | 2 | 2019-03-18 15:29 | 2019-03-22 18:44 | 2 | 0
Standalone URL options into Spirit Galleries | 10 | 9 | 2019-03-19 20:00 | 2019-04-01 19:32 | 9 | 0
Models for fb ad data in fb-backend | 18 | 10 | 2019-01-28 21:15 | 2019-02-20 17:09 | 10 | 0
Setup facebook ad backend project | 217 | 6 | 2019-01-22 19:18 | 2019-11-20 12:30 | 6 | 0
Code for pulling FB ad data I | 12 | 5 | 2019-02-14 21:32 | 2019-03-01 14:55 | 5 | 0
Usage of facebook tokens in fb-backend | 31 | 3 | 2019-02-13 15:11 | 2019-03-27 19:36 | 3 | 0
Mac Server Setup | 14 | 7 | 2019-11-06 14:10 | 2019-11-25 16:07 | 7 | 0
Formulas:
Epic Duration = NETWORKDAYS([Start Date],[End Date])

## LayerCake
Epic Name | Epic Duration | Num of Story | Start Date | End Date | Story No Point | Story Has Points
Connect Facebook in Scheduler (Partnership MVP) | 12 | 3 | 2019-03-18 16:45 | 2019-04-02 11:05 | 3 | 0
Auto publishing for Twitter | 50 | 101 | 2019-01-15 21:24 | 2019-03-25 19:05 | 101 | 0
New admin panel - Phase 1 | 122 | 118 | 2018-12-04 20:25 | 2019-05-22 16:38 | 118 | 0
IG Auto Publish (Web and Mobile) - V1 | 69 | 174 | 2019-05-23 11:21 | 2019-08-27 16:21 | 174 | 0
Support Marketing Moving webpages on dashhudson.com to CMS | 29 | 5 | 2019-07-28 19:24 | 2019-09-05 12:50 | 5 | 0
IG Auto Publish V1: Post Release (Web) | 40 | 12 | 2019-07-29 17:31 | 2019-09-20 10:40 | 12 | 0
Okta Integration (SSO) | 79 | 5 | 2019-07-28 13:55 | 2019-11-14 18:04 | 5 | 0
Twitter Weekly Report | 56 | 18 | 2019-10-24 17:18 | 2020-01-09 18:10 | 18 | 0
Image Cropping (Desktop/Web only) | 27 | 36 | 2019-11-12 13:57 | 2019-12-18 22:05 | 36 | 0
Video Cropping | 41 | 1 | 2019-12-16 19:35 | 2020-02-10 13:10 | 1 | 0
UI Feature Flag Mechanism | 2 | 1 | 2019-03-20 18:55 | 2019-03-21 18:55 | 1 | 0
Models evaluation | 11 | 4 | 2019-02-06 17:03 | 2019-02-20 14:00 | 4 | 0
Formulas:
Epic Duration = NETWORKDAYS([Start Date],[End Date])

## Storm
Epic Name | Epic Duration | Num of Story | Start Date | End Date | Story No Point | Story Has Points
Mobile - Swipe Ups (Target: Feb 28) | 20 | 9 | 2019-02-04 18:27 | 2019-03-01 19:48 | 9 | 0
Mobile - Boards for Stories (Target: Feb 28) | 26 | 14 | 2019-02-07 16:01 | 2019-03-14 14:56 | 14 | 0
Mobile Twitter Auto-Publish | 31 | 76 | 2019-02-03 16:52 | 2019-03-18 14:32 | 76 | 0
Android App MVP (no Story Studio) | 47 | 85 | 2019-03-25 18:05 | 2019-05-28 16:23 | 84 | 1
Mobile Dev Tooling | 0 | 0 | 0 | 0 | 0 | 0
Improve speed of Travis | 0 | 0 | 0 | 0 | 0 | 0
Unscheduled Tab Work Flow on Mobile | 7 | 8 | 2019-05-26 13:39 | 2019-06-04 16:33 | 8 | 0
IG Auto Publish V1: Post Release (Mobile) | 21 | 9 | 2019-08-06 20:28 | 2019-09-03 18:33 | 9 | 0
Pinterest Auto Publish Post Release (Mobile) | 12 | 13 | 2019-08-13 13:41 | 2019-08-28 16:53 | 13 | 0
Mobile App Initialization Refactoring | 20 | 15 | 2019-08-27 12:43 | 2019-09-23 19:03 | 15 | 0
Story Studio Bugs - Mobile | 14 | 11 | 2019-08-25 14:48 | 2019-09-12 16:22 | 7 | 4
Ads Product: FB Ads Enhancement | 53 | 41 | 2019-10-06 18:57 | 2019-12-18 14:58 | 38 | 3
Global pop-up Updates (Boosted Posts) | 32 | 19 | 2019-10-21 16:16 | 2019-12-03 20:43 | 10 | 9
Custom UTM Codes MVP | 29 | 10 | 2019-11-04 17:46 | 2019-12-12 14:38 | 5 | 5
MVP Ads Product | 12 | 13 | 2019-09-16 19:49 | 2019-10-01 15:44 | 2 | 11
Ads Platform - Ads Dashboard | 39 | 21 | 2019-11-20 14:36 | 2020-01-13 19:21 | 12 | 9
Ads Platform - Ads Dashboard: Post Release | 15 | 2 | 2019-12-19 19:01 | 2020-01-08 14:14 | 2 | 0
Facebook Connection Debug Tool | 22 | 15 | 2020-01-14 17:35 | 2020-02-12 13:44 | 7 | 8
Android App Investigation | 0 | 0 | 0 | 0 | 0 | 0
Mobile - Post Status of Scheduled Stories (Target: Feb 18) | 2 | 1 | 2019-01-28 16:55 | 2019-01-29 18:59 | 1 | 0
Mobile Story Studio - 3 Easiest Templates (Target: Feb 11) | 12 | 6 | 2019-01-30 16:11 | 2019-02-14 17:36 | 6 | 0
Formulas:
Epic Duration = NETWORKDAYS([Start Date],[End Date])